## Overview
RC-QASyn Research Implementation Manifest
Plan for a separate quality-aware LLM synthetic-data research repo: literature, datasets, modules, milestones and agent workflow. |  |  | Planning KPI | Value
|  |  | Curated papers | 34
Repository decision | SEPARATE REPO — keep imbalance-synthesis-lab focused on the ML/class-imbalance paper. |  | Tier A papers | 25
Recommended name | quality-aware-synthesis-lab (Python package: rcqasyn) |  | Tier B papers | 9
Reuse strategy | Reuse patterns/utilities intentionally; extract a shared core only later if stable overlap becomes substantial. |  | Dataset rows | 10
Paper collection | Collect now, but from this curated QAxx manifest — not hundreds of random PDFs. |  | Core-including datasets | 7
Reading order | Download/read Tier A first (publication-critical); Tier B is supporting and read on demand. |  | Mapped modules | 18
Scope lock | First publishable version: structured/tabular records, optionally with short textual fields. Avoid all-modality scope creep. |  | Roadmap milestones | 10
Immediate execution sequence
# | Action | Milestone
1 | Create the new repo and copy only the experiment conventions you actually need. | M0
2 | Download Tier A papers into literature/papers/ using QAxx filenames; start agent notes module-by-module. | Literature
3 | Prepare the 3 dev datasets: page-blocks0, Ecoli4 and Abalone19. | Data
4 | Implement B1 Raw LLM, B2 rule filter and B3 single-LLM-judge baselines before advanced components. | M1
5 | Implement a common Evidence interface plus deterministic/statistical/semantic validators. | M2
6 | Only after baseline failure modes are measured, build factual grounding, calibration/fusion, controller and localized repair. | M3–M6
7 | Add dataset-level coverage optimization after record-level quality is stable. | M7
8 | Treat failure memory and cost-aware routing as secondary extensions, not blockers for paper v1. | M8 optional
Publication-core feature lock (do not expand until these work)
1 | Heterogeneous calibrated critic fusion | Novel core
2 | Risk-calibrated acceptance / revalidation | Novel core
3 | Dependency-aware defect-localized repair | Novel core
4 | Dataset-level marginal coverage controller | Novel core
5 | Failure-signature memory | Secondary; add after core evidence

## Paper Manifest
ID | Priority | Category | Modules | Title | Authors | Year | Venue | Type | Why Relevant | Read For | Implementation Use | Landing URL | PDF URL | Suggested Filename | Download Status | Agent Note File | Note Status
QA01 | Tier A | Survey / field map | Literature foundation; full pipeline | On LLMs-Driven Synthetic Data Generation, Curation, and Evaluation: A Survey | Lin Long et al. | 2024 | Findings of ACL 2024 | Peer-reviewed | Best field-level map of LLM synthetic data generation/curation/evaluation; explicitly identifies lack of a unified framework. | Taxonomy, research gaps, generation-curation-evaluation workflow | Use to justify overall thesis framing and literature taxonomy. | https://aclanthology.org/2024.findings-acl.658/ | https://aclanthology.org/2024.findings-acl.658.pdf | qa01-llm-synthetic-data-survey-2024.pdf | Downloaded | literature/notes/QA01.md | Not started
QA02 | Tier B | Survey / annotation | Literature foundation; evaluator design | Large Language Models for Data Annotation and Synthesis: A Survey | Zhen Tan et al. | 2024 | EMNLP 2024 | Peer-reviewed | Broad survey of LLM annotation and synthesis; useful for evaluator/annotation design and data creation workflows. | LLM annotation, synthesis assessment, costs, data types | Use as secondary survey and to map LLM-as-annotator/evaluator literature. | https://aclanthology.org/2024.emnlp-main.54/ | https://aclanthology.org/2024.emnlp-main.54.pdf | qa02-llm-data-annotation-synthesis-survey-2024.pdf | Downloaded | literature/notes/QA02.md | Not started
QA03 | Tier B | Survey / augmentation | Generation; downstream utility | Data Augmentation using LLMs: Data Perspectives, Learning Paradigms and Challenges | Bosheng Ding et al. | 2024 | Findings of ACL 2024 | Peer-reviewed | Useful synthesis of LLM-based augmentation strategies and learning paradigms; complements the main survey with downstream perspective. | Prompting strategies, selection, augmentation paradigms, challenges | Use to motivate baselines and distinguish data-generation quality from downstream training utility. | https://aclanthology.org/2024.findings-acl.97/ | https://aclanthology.org/2024.findings-acl.97.pdf | qa03-llm-data-augmentation-survey-2024.pdf | Downloaded | literature/notes/QA03.md | Not started
QA04 | Tier A | LLM synthetic data | Generation; downstream utility | Synthetic Data Generation with Large Language Models for Text Classification: Potential and Limitations | Zhuoyan Li, Hangxiao Zhu, Zhuoran Lu, Ming Yin | 2023 | EMNLP 2023 | Peer-reviewed | Direct evidence that LLM-generated synthetic data utility is inconsistent across tasks and affected by task/instance subjectivity. | Experimental design, downstream utility, negative/conditional findings | Use to argue that realism alone is insufficient and TSTR/task utility must be measured. | https://aclanthology.org/2023.emnlp-main.647/ | https://aclanthology.org/2023.emnlp-main.647.pdf | qa04-llm-synthetic-text-classification-limitations-2023.pdf | Downloaded | literature/notes/QA04.md | Not started
QA05 | Tier A | LLM generator evaluation | Evaluation; generator benchmarking | Evaluating Language Models as Synthetic Data Generators | Seungone Kim et al. | 2025 | ACL 2025 | Peer-reviewed | AgoraBench provides standardized settings for comparing LMs as data generators and separates problem-solving ability from data-generation ability. | Generator evaluation protocol, intrinsic properties, student-model utility | Use to design controlled generator comparisons and quality-to-utility correlation experiments. | https://aclanthology.org/2025.acl-long.320/ | https://aclanthology.org/2025.acl-long.320.pdf | qa05-agorabench-llm-synthetic-generator-evaluation-2025.pdf | Downloaded | literature/notes/QA05.md | Not started
QA06 | Tier A | LLM tabular generator | Generator baseline | Language Models are Realistic Tabular Data Generators | Vadim Borisov, Kathrin Seßler, Tobias Leemann, Martin Pawelczyk, Gjergji Kasneci | 2023 | ICLR 2023 | Peer-reviewed | Foundational LLM-based tabular synthesis method (GReaT); important baseline for structured/tabular generation. | Tabular-to-text encoding, conditional generation, ML efficacy | Implement or reproduce as one LLM/transformer generator baseline. | https://openreview.net/forum?id=cEygmQNOeI | https://openreview.net/pdf?id=cEygmQNOeI | qa06-great-language-model-tabular-generator-2023.pdf | Downloaded | literature/notes/QA06.md | Not started
QA07 | Tier B | Transformer tabular generator | Generator baseline; privacy/overfit | REaLTabFormer: Generating Realistic Relational and Tabular Data using Transformers | Aivin V. Solatorio, Olivier Dupriez | 2023 | arXiv 2023 | Influential preprint | Transformer-based tabular/relational synthesizer with target masking and an overfitting statistic. | Autoregressive tabular generation, relational generation, overfitting detection | Optional stronger transformer baseline; useful for privacy/generalization comparisons. | https://arxiv.org/abs/2302.02041 | https://arxiv.org/pdf/2302.02041 | qa07-realtabformer-2023.pdf | Downloaded | literature/notes/QA07.md | Not started
QA08 | Tier B | GAN tabular generator | Generator baseline | Modeling Tabular Data using Conditional GAN | Lei Xu, Maria Skoularidou, Alfredo Cuesta-Infante, Kalyan Veeramachaneni | 2019 | NeurIPS 2019 | Foundational peer-reviewed | CTGAN is a foundational mixed-type tabular generator and still a useful classical deep-generative baseline. | Mixed-type modeling, imbalance in categorical variables, ML efficacy | Use as non-LLM GAN baseline and for mixed-type benchmark comparison. | https://proceedings.neurips.cc/paper/2019/hash/254ed7d2de3b23ab10936522dd547b78-Abstract.html | https://proceedings.neurips.cc/paper/2019/file/254ed7d2de3b23ab10936522dd547b78-Paper.pdf | qa08-ctgan-2019.pdf | Downloaded | literature/notes/QA08.md | Not started
QA09 | Tier B | Diffusion tabular generator | Generator baseline | TabDDPM: Modelling Tabular Data with Diffusion Models | Akvilė Kotelnikov et al. | 2023 | ICML 2023 | Peer-reviewed | Strong diffusion baseline designed for heterogeneous tabular data. | Diffusion for numerical/categorical columns, fidelity, ML efficacy | Use as representative diffusion baseline. | https://proceedings.mlr.press/v202/kotelnikov23a.html | https://proceedings.mlr.press/v202/kotelnikov23a/kotelnikov23a.pdf | qa09-tabddpm-2023.pdf | Downloaded | literature/notes/QA09.md | Not started
QA10 | Tier B | Graph tabular generator | Generator baseline; dependency modeling | GOGGLE: Generative Modelling for Tabular Data by Learning Relational Structure | Tennison Liu, Zhaozhi Qian, Jeroen Berrevoets, Mihaela van der Schaar | 2023 | ICLR 2023 | Peer-reviewed | Explicitly learns variable relationships, making it relevant to cross-field consistency and structured dependencies. | Relational structure, functional dependencies, prior knowledge | Useful baseline/reference for dependency-aware validation and generation. | https://openreview.net/forum?id=fPVRcJqspu | https://openreview.net/pdf?id=fPVRcJqspu | qa10-goggle-relational-tabular-generation-2023.pdf | Downloaded | literature/notes/QA10.md | Not started
QA11 | Tier A | Diffusion tabular generator | Generator baseline | Mixed-Type Tabular Data Synthesis with Score-based Diffusion in Latent Space | Hengrui Zhang et al. | 2024 | ICLR 2024 | Peer-reviewed | TabSyn is a strong modern mixed-type tabular baseline with fidelity, correlation and ML-efficacy evaluation. | Latent diffusion, mixed types, pairwise correlations, α-precision/β-recall | Primary non-LLM generator baseline for the final paper. | https://proceedings.iclr.cc/paper_files/paper/2024/hash/e9750610639c3e7a849cff746bf60dbd-Abstract-Conference.html | https://proceedings.iclr.cc/paper_files/paper/2024/file/e9750610639c3e7a849cff746bf60dbd-Paper-Conference.pdf | qa11-tabsyn-2024.pdf | Downloaded | literature/notes/QA11.md | Not started
QA12 | Tier A | LLM tabular / imbalance | Generator baseline; prompting; class imbalance | EPIC: Effective Prompting for Imbalanced-Class Data Synthesis in Tabular Data Classification via Large Language Models | Jinhee Kim, Taesung Kim, Jaegul Choo | 2024 | NeurIPS 2024 | Peer-reviewed | Directly overlaps our structured-data setting: LLM in-context generation for imbalanced tabular classification. | Prompt design, class balance, grouping, correlations, efficiency | Critical baseline/reference because it is the closest LLM-tabular class-imbalance work. | https://proceedings.neurips.cc/paper_files/paper/2024/hash/37f2f382b1e1f1e887d610e7ea047086-Abstract-Conference.html | https://proceedings.neurips.cc/paper_files/paper/2024/file/37f2f382b1e1f1e887d610e7ea047086-Paper-Conference.pdf | qa12-epic-llm-imbalanced-tabular-synthesis-2024.pdf | Downloaded | literature/notes/QA12.md | Not started
QA13 | Tier A | Constraint-based generation | Deterministic validation; constraint compiler | How Realistic Is Your Synthetic Data? Constraining Deep Generative Models for Tabular Data | Mihaela Cătălina Stoian, Salijona Dyrmishi, Maxime Cordy, Thomas Lukasiewicz, Eleonora Giunchiglia | 2024 | ICLR 2024 | Peer-reviewed | Shows how domain constraints can be parsed and enforced in deep tabular generators; central to our deterministic validation/constraint module. | Constraint language, hard compliance, train-time vs inference-time guardrails | Use to design ConstraintCompiler and distinguish guaranteed constraints from probabilistic critics. | https://proceedings.iclr.cc/paper_files/paper/2024/hash/887932131fddf943e8fe3310b62c0147-Abstract-Conference.html | https://proceedings.iclr.cc/paper_files/paper/2024/file/887932131fddf943e8fe3310b62c0147-Paper-Conference.pdf | qa13-constrained-tabular-generative-models-2024.pdf | Downloaded | literature/notes/QA13.md | Not started
QA14 | Tier A | Synthetic quality metrics | Quality model; dataset audit | How Faithful is your Synthetic Data? Sample-level Metrics for Evaluating and Auditing Generative Models | Ahmed M. Alaa, Boris van Breugel, Evgeny Saveliev, Mihaela van der Schaar | 2022 | ICML 2022 | Foundational peer-reviewed | Separates fidelity, diversity and authenticity; especially useful because metrics can operate at sample level for auditing. | α-Precision, β-Recall, Authenticity, sample-level auditing | Primary foundation for multidimensional quality and record-level audit metrics. | https://proceedings.mlr.press/v162/alaa22a.html | https://proceedings.mlr.press/v162/alaa22a/alaa22a.pdf | qa14-faithful-synthetic-data-metrics-2022.pdf | Downloaded | literature/notes/QA14.md | Not started
QA15 | Tier A | Synthetic data methodology | Evaluation; uncertainty; downstream use | Synthetic Data, Real Errors: How (Not) to Publish and Use Synthetic Data | Boris van Breugel, Zhaozhi Qian, Mihaela van der Schaar | 2023 | ICML 2023 | Peer-reviewed | Important cautionary paper: synthetic data should not be treated like real data; discusses generalization/error implications and publication/use practices. | Uncertainty, downstream evaluation, systemic synthetic-data errors | Use to justify hold-out real testing, explicit uncertainty and reporting discipline. | https://proceedings.mlr.press/v202/van-breugel23a.html | https://proceedings.mlr.press/v202/van-breugel23a/van-breugel23a.pdf | qa15-synthetic-data-real-errors-2023.pdf | Downloaded | literature/notes/QA15.md | Not started
QA16 | Tier A | Data-centric synthetic generation | Dataset-level optimization; evaluation | Reimagining Synthetic Tabular Data Generation through Data-Centric AI: A Comprehensive Benchmark | Lasse Hansen, Nabeel Seedat, Mihaela van der Schaar, Andrija Petrovic | 2023 | NeurIPS 2023 Datasets & Benchmarks | Peer-reviewed | Direct precedent for profiling data to guide synthesis and evaluating synthetic tabular data through a data-centric lens. | Data profiles, generator selection/guidance, comprehensive benchmark | Central reference for dataset-level feedback and data-centric optimization. | https://proceedings.neurips.cc/paper_files/paper/2023/hash/6aa9a05b929fb08ff46a58cab6cf860d-Abstract-Datasets_and_Benchmarks.html | https://proceedings.neurips.cc/paper_files/paper/2023/file/6aa9a05b929fb08ff46a58cab6cf860d-Paper-Datasets_and_Benchmarks.pdf | qa16-data-centric-synthetic-tabular-benchmark-2023.pdf | Downloaded | literature/notes/QA16.md | Not started
QA17 | Tier A | Adaptive data generation | Dataset controller; weak-region feedback | Targeted Data Generation: Finding and Fixing Model Weaknesses | Zexue He, Marco Tulio Ribeiro, Fereshte Khani | 2023 | ACL 2023 | Peer-reviewed | Automatically identifies challenging subgroups and targets generation toward them; strong precedent for dataset-level feedback. | Weak subgroups, targeted generation, human-in-the-loop | Use to motivate marginal coverage/rare-region controller and generation targeting. | https://aclanthology.org/2023.acl-long.474/ | https://aclanthology.org/2023.acl-long.474.pdf | qa17-targeted-data-generation-2023.pdf | Downloaded | literature/notes/QA17.md | Not started
QA18 | Tier A | Hallucination detection | Factual validator; uncertainty | SelfCheckGPT: Zero-Resource Black-Box Hallucination Detection for Generative Large Language Models | Potsawee Manakul, Adian Liusie, Mark J. F. Gales | 2023 | EMNLP 2023 | Peer-reviewed | Sampling-based self-consistency detector requiring no external KB; useful as one evidence source, not a final truth oracle. | Sampling, contradiction/consistency, black-box hallucination detection | Implement as optional factual uncertainty signal in validator ensemble. | https://aclanthology.org/2023.emnlp-main.557/ | https://aclanthology.org/2023.emnlp-main.557.pdf | qa18-selfcheckgpt-2023.pdf | Downloaded | literature/notes/QA18.md | Not started
QA19 | Tier A | Factuality evaluation | Atomic factual validator | FActScore: Fine-grained Atomic Evaluation of Factual Precision in Long Form Text Generation | Sewon Min et al. | 2023 | EMNLP 2023 | Peer-reviewed | Breaks generations into atomic facts and checks support against reliable knowledge sources. | Claim decomposition, evidence retrieval, fact-level support | Key design reference for field/claim-level factual validation and provenance. | https://aclanthology.org/2023.emnlp-main.741/ | https://aclanthology.org/2023.emnlp-main.741.pdf | qa19-factscore-2023.pdf | Downloaded | literature/notes/QA19.md | Not started
QA20 | Tier A | Fact-level hallucination / repair | Localized defects; repair | FactSelfCheck: Fact-Level Black-Box Hallucination Detection for LLMs | Albert Sawczyn, Jakub Binkowski, Denis Janiak, Bogdan Gabrys, Tomasz Kajdanowicz | 2026 | Findings of EACL 2026 | Peer-reviewed | Recent fine-grained fact-level detection using interpretable triples; especially relevant to localized correction. | Fact triples, fine-grained detection, correction | Use as closest precedent for defect localization and fine-grained repair. | https://aclanthology.org/2026.findings-eacl.296/ | https://aclanthology.org/2026.findings-eacl.296.pdf | qa20-factselfcheck-2026.pdf | Downloaded | literature/notes/QA20.md | Not started
QA21 | Tier A | Uncertainty estimation | Uncertainty module; revalidate decision | Detecting Hallucinations in Large Language Models Using Semantic Entropy | Sebastian Farquhar, Jannik Kossen, Lorenz Kuhn, Yarin Gal | 2024 | Nature 2024 | Peer-reviewed journal | Estimates uncertainty over semantic meanings rather than strings; supports separating quality from evaluator confidence. | Semantic entropy, abstention, uncertainty calibration | Use to design REVALIDATE/abstain behavior and uncertainty features. | https://www.nature.com/articles/s41586-024-07421-0 | https://www.nature.com/articles/s41586-024-07421-0.pdf | qa21-semantic-entropy-hallucination-2024.pdf | Downloaded | literature/notes/QA21.md | Not started
QA22 | Tier A | Verification / iterative correction | Repair; revalidation | Chain-of-Verification Reduces Hallucination in Large Language Models | Shehzaad Dhuliawala et al. | 2024 | Findings of ACL 2024 | Peer-reviewed | Separates initial generation from independent verification questions and revision. | Verification planning, independent checking, revision | Reference for separating generation and verification pathways. | https://aclanthology.org/2024.findings-acl.212/ | https://aclanthology.org/2024.findings-acl.212.pdf | qa22-chain-of-verification-2024.pdf | Downloaded | literature/notes/QA22.md | Not started
QA23 | Tier A | Tool-grounded correction | Repair agent; external validation | CRITIC: Large Language Models Can Self-Correct with Tool-Interactive Critiquing | Zhibin Gou et al. | 2024 | ICLR 2024 | Peer-reviewed | Shows self-correction driven by external tool feedback rather than introspection alone. | Tool use, critique, iterative correction | Central reference for evidence-grounded RepairAgent design. | https://proceedings.iclr.cc/paper_files/paper/2024/hash/fef126561bbf9d4467dbb8d27334b8fe-Abstract-Conference.html | https://proceedings.iclr.cc/paper_files/paper/2024/file/fef126561bbf9d4467dbb8d27334b8fe-Paper-Conference.pdf | qa23-critic-tool-interactive-self-correction-2024.pdf | Downloaded | literature/notes/QA23.md | Not started
QA24 | Tier A | Self-correction limitations | Controller design; external evidence necessity | Large Language Models Cannot Self-Correct Reasoning Yet | Jie Huang et al. | 2024 | ICLR 2024 | Peer-reviewed | Critical counterpoint showing intrinsic self-correction can fail or degrade without external feedback. | Intrinsic self-correction failure modes | Use to justify heterogeneous/external validators and avoid generator-as-sole-critic designs. | https://openreview.net/forum?id=IkmD3fKBPQ | https://openreview.net/pdf?id=IkmD3fKBPQ | qa24-llms-cannot-self-correct-reasoning-yet-2024.pdf | Downloaded | literature/notes/QA24.md | Not started
QA25 | Tier B | Retrieval + self-reflection | Grounding planner; RAG | Self-RAG: Learning to Retrieve, Generate, and Critique through Self-Reflection | Akari Asai, Zeqiu Wu, Yizhong Wang, Avirup Sil, Hannaneh Hajishirzi | 2024 | ICLR 2024 | Peer-reviewed | Conditional retrieval and reflection; useful for deciding when grounding is necessary. | Retrieval routing, reflection tokens, evidence use | Reference for GroundingPlanner and conditional retrieval rather than always-on RAG. | https://proceedings.iclr.cc/paper_files/paper/2024/hash/25f7be9694d7b32d5cc670927b8091e1-Abstract-Conference.html | https://proceedings.iclr.cc/paper_files/paper/2024/file/25f7be9694d7b32d5cc670927b8091e1-Paper-Conference.pdf | qa25-self-rag-2024.pdf | Downloaded | literature/notes/QA25.md | Not started
QA26 | Tier A | RAG hallucination | Factual validator; evidence entailment | RAGTruth: A Hallucination Corpus for Developing Trustworthy Retrieval-Augmented Language Models | Cheng Niu et al. | 2024 | ACL 2024 | Peer-reviewed | Demonstrates that RAG outputs can remain unsupported or contradictory to retrieved evidence. | Span-level hallucination, RAG evaluation, claim-evidence mismatch | Use to require explicit evidence entailment rather than treating retrieval as correctness. | https://aclanthology.org/2024.acl-long.585/ | https://aclanthology.org/2024.acl-long.585.pdf | qa26-ragtruth-2024.pdf | Downloaded | literature/notes/QA26.md | Not started
QA27 | Tier A | LLM-as-a-judge | LLM critic; evaluator bias | Judging LLM-as-a-Judge with MT-Bench and Chatbot Arena | Lianmin Zheng et al. | 2023 | NeurIPS 2023 Datasets & Benchmarks | Peer-reviewed | Foundational LLM-as-judge work; documents position, verbosity and self-enhancement biases. | Judge agreement, bias, rubric design | Use to design narrow rubric critics and justify heterogeneous critic ensemble. | https://proceedings.neurips.cc/paper_files/paper/2023/hash/91f18a1287b398d378ef22505bf41832-Abstract-Datasets_and_Benchmarks.html | https://proceedings.neurips.cc/paper_files/paper/2023/file/91f18a1287b398d378ef22505bf41832-Paper-Datasets_and_Benchmarks.pdf | qa27-llm-as-a-judge-mtbench-2023.pdf | Downloaded | literature/notes/QA27.md | Not started
QA28 | Tier A | Calibration / conformal | Evidence fusion; risk gate | Language Models with Conformal Factuality Guarantees | Christopher Mohri, Tatsunori Hashimoto | 2024 | ICML 2024 | Peer-reviewed | Connects factuality to uncertainty quantification and conformal prediction; strongest theoretical reference for risk-calibrated acceptance. | Conformal prediction, correctness guarantees, calibration | Core reference for RiskCalibrator and target defect-rate acceptance gate. | https://proceedings.mlr.press/v235/mohri24a.html | https://proceedings.mlr.press/v235/mohri24a/mohri24a.pdf | qa28-conformal-factuality-2024.pdf | Downloaded | literature/notes/QA28.md | Not started
QA29 | Tier B | LLM evaluator training | LLM critic; factual consistency | TrueTeacher: Learning Factual Consistency Evaluation with Large Language Models | Zorik Gekhman, Jonathan Herzig, Roee Aharoni, Chen Elkind, Idan Szpektor | 2023 | EMNLP 2023 | Peer-reviewed | Uses LLM annotations to train a factual consistency evaluator; relevant to distilling expensive critics into cheaper validators. | Factual consistency, synthetic evaluator training, NLI | Optional reference for lightweight learned critic or evaluator distillation. | https://aclanthology.org/2023.emnlp-main.127/ | https://aclanthology.org/2023.emnlp-main.127.pdf | qa29-trueteacher-factual-consistency-2023.pdf | Downloaded | literature/notes/QA29.md | Not started
QA30 | Tier A | Data inconsistency localization | Semantic/statistical validator; localized repair | DAGnosis: Localized Identification of Data Inconsistencies using Structures | Nicolas Huynh et al. | 2024 | AISTATS 2024 | Peer-reviewed | Data-centric method that localizes why a tabular sample is inconsistent using structure; directly relevant to defect maps. | Structural dependencies, inconsistency localization, auditability | Key reference for field-level defect localization and dependency graph validation. | https://proceedings.mlr.press/v238/huynh24a.html | https://proceedings.mlr.press/v238/huynh24a/huynh24a.pdf | qa30-dagnosis-localized-data-inconsistency-2024.pdf | Downloaded | literature/notes/QA30.md | Not started
QA31 | Tier A | Privacy | Privacy validator; authenticity | Membership Inference Attacks against Synthetic Data through Overfitting Detection | Boris van Breugel, Hao Sun, Zhaozhi Qian, Mihaela van der Schaar | 2023 | AISTATS 2023 | Peer-reviewed | Shows synthetic data can leak training membership and provides a practical attack framework. | Membership inference, overfitting, privacy risk | Core privacy audit reference for MIA and memorization tests. | https://proceedings.mlr.press/v206/breugel23a.html | https://proceedings.mlr.press/v206/breugel23a/breugel23a.pdf | qa31-membership-inference-synthetic-data-2023.pdf | Downloaded | literature/notes/QA31.md | Not started
QA32 | Tier A | Fairness | Fairness validator; constrained optimization | Imposing Fairness Constraints in Synthetic Data Generation | Mahed Abroshan, Andrew Elliott, Mohammad Mahdi Khalili | 2024 | AISTATS 2024 | Peer-reviewed | Formalizes fairness in synthetic data generation and shows frameworks for counterfactual/information-filtering fairness. | Fairness definitions, constraints, fairness-fidelity trade-offs | Core reference for task-specific fairness contract and fairness constraints. | https://proceedings.mlr.press/v238/abroshan24a.html | https://proceedings.mlr.press/v238/abroshan24a/abroshan24a.pdf | qa32-fairness-constraints-synthetic-data-2024.pdf | Downloaded | literature/notes/QA32.md | Not started
QA33 | Tier B | Bias feedback loops | Fairness; dataset-level feedback | Fairness Feedback Loops: Training on Synthetic Data Amplifies Bias | Sierra Wyllie, Ilia Shumailov, Nicolas Papernot | 2024 | ACM FAccT 2024 | Peer-reviewed | Shows synthetic/model-induced feedback loops can reduce fairness and minoritized-group representation over generations. | Bias amplification, representation loss, feedback loops | Use to motivate subgroup monitoring and failure/feedback safeguards. | https://dl.acm.org/doi/10.1145/3630106.3659029 | https://dl.acm.org/doi/pdf/10.1145/3630106.3659029 | qa33-fairness-feedback-loops-synthetic-data-2024.pdf | Downloaded | literature/notes/QA33.md | Not started
QA34 | Tier A | Diversity / model collapse | Dataset optimizer; rare-mode coverage | AI Models Collapse When Trained on Recursively Generated Data | Ilia Shumailov et al. | 2024 | Nature 2024 | Peer-reviewed journal | Demonstrates progressive loss of tail information and variance under recursive synthetic training. | Tail loss, model collapse, distribution shrinkage | Core motivation for rare-mode coverage, diversity feedback and retaining real reference anchors. | https://www.nature.com/articles/s41586-024-07566-y | https://www.nature.com/articles/s41586-024-07566-y.pdf | qa34-model-collapse-recursive-synthetic-data-2024.pdf | Downloaded | literature/notes/QA34.md | Not started

## Module Mapping
Module | Layer | Paper IDs | Purpose / Research Role | Primary Output | Paper Priority
TaskContract / ConstraintCompiler | Specification | QA01, QA13 | Define schema, hard/soft constraints, sensitive attributes and dependency graph. | Quality contract + executable constraint registry | Core
Generator adapters | Generation | QA04, QA05, QA06, QA07, QA08, QA09, QA10, QA11, QA12 | Model-agnostic generation interface; begin with one LLM and add generator baselines later. | Generator.generate() + provenance metadata | Core
Deterministic validator | Record validation | QA13 | Schema, types, ranges, regex, cross-field and referential constraints. | Deterministic Evidence objects | Core
Statistical validator | Record + dataset validation | QA14, QA15, QA16, QA30 | Outlier, support, marginal/joint distribution and anomaly diagnostics. | Statistical Evidence + dataset audit metrics | Core
Semantic / NLI validator | Record validation | QA18, QA20, QA29, QA30 | Cross-field contradiction, semantic coherence and textual relation checks. | Semantic Evidence object | Core
Factual / RAG validator | Record validation | QA18, QA19, QA20, QA25, QA26 | Atomic claim extraction, retrieval, provenance and support/contradict/unknown verification. | Fact Evidence with source IDs | Core
Rubric-specific LLM critic | Record validation | QA27, QA29 | Use an LLM only for narrow contextual rubrics instead of a monolithic 1–10 quality score. | Critic Evidence + raw confidence | Core
Uncertainty / calibration | Fusion | QA21, QA28 | Separate quality from confidence; calibrate defect probabilities and acceptance risk. | Calibrated risk + ECE/Brier metrics | Core
Heterogeneous evidence fusion | Fusion | QA27, QA28, QA30 | Fuse deterministic, statistical, semantic, factual and LLM evidence; model disagreement explicitly. | Per-dimension defect risk vector | Novel Core
Decision controller | Control | QA22, QA23, QA24, QA28 | Choose ACCEPT / REPAIR / REVALIDATE / REGENERATE / REJECT with finite budgets. | Action + reason + cost log | Novel Core
Defect-localized repair | Repair | QA20, QA22, QA23, QA30 | Repair minimal failed field/claim subgraph while freezing validated fields. | Patched record + mutation provenance | Novel Core
Duplicate / diversity evaluator | Dataset optimization | QA14, QA16, QA34 | Exact and semantic duplicate detection, coverage, entropy and rare-mode recall. | Marginal contribution features | Core
Dataset-level coverage optimizer | Dataset optimization | QA16, QA17, QA34 | Accept/target candidates based on marginal coverage and rare/subgroup deficits after integrity gates. | Selected dataset + next-generation targets | Novel Core
Privacy validator | Risk audit | QA14, QA15, QA31 | PII, exact/near-copy checks, nearest-neighbor risk and membership-inference experiments. | Privacy risk evidence | Core
Fairness validator | Risk audit | QA32, QA33 | Task-specific subgroup representation, outcome and counterfactual checks. | Fairness report + subgroup gaps | Core where applicable
Failure-signature memory | Feedback | QA24, QA33, QA34 | Store abstract recurrent defect signatures and feed high-frequency failures back to generation. | Versioned failure memory | Optional / Secondary
Cost-aware validator routing | Efficiency | QA21, QA27, QA28 | Use cheap-first validation and escalate uncertain/high-risk records. | Calls/tokens/latency + routing policy | Secondary
Downstream utility evaluator | Evaluation | QA04, QA05, QA14, QA15, QA16 | TSTR/TRTR/augmentation and quality–utility correlation across multiple learners. | Utility metrics + quality-cost frontier | Core

## Dataset Plan
Dataset | Role | Source | n | p | Imbalance Ratio | Feature Types | Missing | Benchmark Purpose | Why Selected | Source URL | Download Status | Local Folder
page-blocks0 | Development only | KEEL | 5472 | 10 | 8.79 | Numeric | No | Fast development benchmark | Medium size and moderate imbalance; good for smoke runs before full suites. | https://sci2s.ugr.es/keel/category.php?cat=imb&order=insR | Not downloaded | data/raw/page-blocks0/
Ecoli4 | Development + Core | KEEL | 336 | 7 | 15.8 | Numeric | No | Small-data / minority-scarcity stress | Tests whether learned generators and repair policies remain stable with very little data. | https://sci2s.ugr.es/keel/category.php?cat=imb&order=insR | Not downloaded | data/raw/ecoli4/
Abalone19 | Development + Core | KEEL | 4174 | 8 | 129.44 | Mixed/encoded | No | Extreme-imbalance stress | ~0.77% positive in the source workbook; tests severe minority scarcity and distribution-estimation error. | https://sci2s.ugr.es/keel/dataset.php?cod=115 | Not downloaded | data/raw/abalone19/
HTRU2 | Core | UCI | 17898 | 8 | 9.92 | Numeric | No | Real-world moderate rare-event anchor | Genuine pulsar rare-event task; provides a credible non-transformed real-world benchmark. | https://archive.ics.uci.edu/dataset/372/htru2 | Not downloaded | data/raw/htru2/
Musk | Core | ODDS | 3062 | 166 | 30.6 | Numeric | No | High-dimensional stress | Tests whether geometry-based and learned/latent generators remain reliable at high feature dimension. | https://shebuti.com/outlier-detection-datasets-odds/ | Not downloaded | data/raw/musk/
Mammography | Core | ODDS | 11183 | 6 | 42 | Numeric | No | Severe-imbalance low-dimensional anchor | Separates severe imbalance effects from high-dimensionality effects. | https://shebuti.com/outlier-detection-datasets-odds/ | Not downloaded | data/raw/mammography/
Bank Marketing | Core | UCI | 45211 | 16 | 7.55 | Mixed categorical+numeric | No | Mixed-type tabular benchmark | Essential for testing LLM/CTGAN/diffusion-style generators on categorical + numerical dependencies. | https://archive.ics.uci.edu/dataset/222/bank+marketing | Not downloaded | data/raw/bank_marketing/
Default of Credit Card Clients | Core / Control | UCI | 30000 | 23 | 3.5 | Mixed/encoded | No | Mild-imbalance control | Tests whether the controller can avoid unnecessary generation/repair when class imbalance is modest. | https://archive.ics.uci.edu/dataset/350/default+of+credit+card+clients | Not downloaded | data/raw/default_credit/
APS Failure at Scania Trucks | Optional Stress | UCI | 60000 | 171 | 59 | Numeric | Yes | Industrial hard mode | Combines scale, high dimension, severe imbalance and missing values; useful after core pipeline stabilizes. | https://archive.ics.uci.edu/ml/datasets/aps%2Bfailure%2Bat%2Bscania%2Btrucks | Not downloaded | data/raw/aps_failure/
Satimage-2 | Optional Stress | ODDS | 5803 | 36 | 80.7 | Numeric | No | Extreme-IR replication | Adds a second extreme-imbalance stress case to test whether Abalone19 results generalize. | https://shebuti.com/outlier-detection-datasets-odds/ | Not downloaded | data/raw/satimage2/

## Implementation Roadmap
Milestone | Name | Priority | Status | Objective | Deliverables | Exit Criteria | Depends On | Key Papers | Estimated Effort
M0 | Repo + scope contract | Now | Not started | Create separate RC-QASyn repo; lock structured/tabular scope; add manifests, configs and contracts. | Repo skeleton; TaskContract; dataset registry; paper manifest; reproducible config layout. | Package imports; config validation passes; selected datasets resolve through registry. | — | QA01, QA13 | 1–2 days
M1 | Baseline generation + evaluation harness | Now | Not started | Implement raw LLM generation and the first three baselines before advanced agents. | B1 Raw LLM; B2 rules; B3 single LLM judge; provenance; fidelity/validity/diversity/TSTR/cost metrics. | One command produces raw candidates, curated datasets and baseline metric artifacts on dev datasets. | M0 | QA04, QA05, QA06, QA14, QA15, QA16, QA27 | 3–5 days
M2 | Unified validator interface | Next | Not started | Standardize evidence from deterministic, statistical and semantic validators. | Validator.validate(); Evidence schema; deterministic rules; anomaly/statistical checks; semantic/NLI adapter. | All validators emit the same typed Evidence object; unit tests cover known failure fixtures. | M1 | QA13, QA14, QA18, QA29, QA30 | 4–6 days
M3 | Grounding + factual/privacy/fairness adapters | Next | Not started | Add evidence-grounded factual checking and risk-specific validators without yet fusing them. | Claim decomposition; retrieval provenance; entail/contradict/unknown; privacy checks; fairness adapter. | Factual validator preserves evidence IDs; privacy/fairness reports are reproducible and separately switchable. | M2 | QA18, QA19, QA20, QA25, QA26, QA31, QA32 | 5–8 days
M4 | Calibration + heterogeneous evidence fusion | Publication core | Not started | Calibrate validator outputs and learn/implement critic fusion with explicit disagreement. | Calibration set format; per-critic calibration; fused critical-defect risk; Brier/ECE/AUPRC reports. | Fusion beats or matches the best single critic on defect detection and improves calibration/false-accept rate. | M2, M3 | QA21, QA27, QA28, QA30 | 5–8 days
M5 | Finite adaptive decision controller | Publication core | Not started | Implement ACCEPT / REPAIR / REVALIDATE / REGENERATE / REJECT using quality, risk, confidence and cost. | Controller policy; budgets; stopping rules; action logs; revalidation router. | No infinite loops; every action is reproducible; controller ablation can replace calibrated risk with static thresholds. | M4 | QA21, QA22, QA23, QA24, QA28 | 4–6 days
M6 | Dependency-aware localized repair | Publication core | Not started | Repair only defective fields/claims and their dependent subgraph while freezing validated content. | Defect map; dependency graph; constrained RepairAgent; targeted revalidation. | Paired benchmark compares targeted repair vs full regeneration on validity, semantic drift, diversity, tokens and latency. | M5 | QA20, QA22, QA23, QA30 | 5–8 days
M7 | Dataset-level diversity + coverage controller | Publication core | Not started | Move from independent record acceptance to marginal dataset contribution and targeted missing-region generation. | Exact/semantic dedup; cluster/rare-mode coverage; subgroup deficits; marginal contribution score; optimizer. | Ablation demonstrates coverage/redundancy effects without materially increasing critical validity errors. | M5 | QA16, QA17, QA34 | 6–10 days
M8 | Failure memory + cost-aware routing | Optional extension | Not started | Add structured anti-recurrence memory and cheap-first validator escalation after the core paper is working. | Failure signature store; decay/versioning; validator router; recurrence and quality-cost metrics. | Separate ablations show whether recurrence falls and whether routing preserves quality at lower cost. | M5, M7 | QA24, QA33, QA34 | 4–7 days
M9 | Full experiments + paper tables | Final | Not started | Run 7 core datasets, optional stresses, baselines, ablations, repeated seeds, stats and quality-cost frontiers. | Final manifests; raw artifacts; aggregate tables; plots; statistical tests; reproducibility bundle. | All paper claims trace to versioned configs, seeds, source data and stored audit logs. | M1–M7 (M8 optional) | All relevant | 1–3 weeks

## Agent Protocol
Step | Protocol | Agent Instruction | Expected Output | Guardrail
1 | Download by manifest, not by random browsing | Download Tier A first using the exact PDF URL or landing page. Save with the Suggested Filename. | A deterministic local literature set whose filenames match the manifest. | Do not rename ad hoc. Do not mix with ML-paper Pxx files.
2 | Update manifest status | Set Download Status to Downloaded immediately after the PDF is placed in literature/papers/. | The manifest reflects the local paper library. | One row per paper; preserve QAxx ID.
3 | Create one structured note per paper | Write literature/notes/QAxx.md after first read. | A 1–2 page distilled note usable by future agents. | Capture: central idea; problem addressed; generation/post-generation stage; algorithm; datasets/metrics; limitations; reusable concepts; exact module mapping; important equations/figures/pages; citation.
4 | Read on demand | For each implementation task, start from the relevant notes and open only the 3–6 papers mapped to that module. | Focused context instead of repeatedly reading 34 PDFs. | Never prompt an agent to 'read every paper before coding'.
5 | Separate established work from proposed mechanisms | In design docs and code comments, explicitly tag literature-derived mechanisms vs RC-QASyn proposals. | Cleaner novelty claims and fewer accidental citation errors. | Do not claim invention of RAG, validation, self-correction, calibration or synthetic-data metrics.
6 | Extract implementation contracts, not just summaries | Every paper note should end with 'What this changes in our repo'. | Concrete interfaces, metrics, baselines or ablations. | A paper that does not influence design/evaluation can remain Tier B/supporting.
7 | Preserve exact provenance | Store title, venue, year, source URL and citation metadata in the note and manifest. | Paper trail ready for LaTeX/BibTeX later. | Use primary source landing pages whenever possible.
8 | Do not commit large raw literature/data by default | Keep PDFs and raw datasets local or in LFS/external storage unless repository policy deliberately includes them. | Lean source repository with reproducible download manifests. | Commit manifests, notes, hashes/scripts and licenses; review distribution rights before committing PDFs.
9 | Lock experiments before full runs | Each experiment config must declare dataset version, generator, validators, thresholds/calibration, controller, seed and budget. | Reproducible baseline/ablation comparisons. | Do not tune on the real test split.
10 | Audit claims against held-out evidence | Use independent final auditors and untouched real test data for TSTR. | Reduced metric gaming and circular evaluation. | The same validator that drove regeneration should not be the only final quality judge.

## Repo Layout
Decision | Use a separate repository: quality-aware-synthesis-lab (package name rcqasyn). Keep imbalance-synthesis-lab as the ML/class-imbalance paper.
Why separate | Different research question, dependency stack, evaluation framework, paper boundary and reproducibility story.
Reuse policy | Initially copy/adapt only stable utilities (dataset loaders, metrics patterns, experiment conventions). Extract a shared package only after stable overlap is obvious.
Shared-package trigger | Consider synthetic-data-bench-core only if roughly 20–30% of stable code is genuinely shared across both projects; do not create it upfront.
Paper storage | literature/papers/ — local or LFS/external; filenames must match QAxx manifest.
Paper notes | literature/notes/QAxx.md — committed distilled notes.
Raw data | data/raw/ — gitignored; manifests/scripts committed.
Experiment outputs | results/ or artifacts/ — versioned metadata + compact tables committed; large intermediates external/gitignored.
Recommended Repository Layout
quality-aware-synthesis-lab/ ├── README.md ├── pyproject.toml ├── configs/ │ ├── datasets/ │ ├── generators/ │ ├── validators/ │ └── experiments/ ├── data/ │ ├── raw/ # gitignored │ ├── processed/ # gitignored │ └── manifests/ ├── literature/ │ ├── manifest.xlsx │ ├── papers/ # local/LFS; QAxx filenames │ └── notes/ # QAxx.md distilled notes ├── src/rcqasyn/ │ ├── contracts/ │ ├── generators/ │ ├── retrieval/ │ ├── validators/ │ │ ├── deterministic.py │ │ ├── statistical.py │ │ ├── semantic.py │ │ ├── factual.py │ │ ├── llm_critic.py │ │ ├── privacy.py │ │ └── fairness.py │ ├── fusion/ │ │ ├── calibration.py │ │ └── evidence_fusion.py │ ├── controller/ │ │ ├── policy.py │ │ └── budget.py │ ├── repair/ │ │ ├── defect_map.py │ │ ├── dependency_graph.py │ │ └── repair_agent.py │ ├── dataset/ │ │ ├── duplicates.py │ │ ├── diversity.py │ │ ├── coverage.py │ │ ├── optimizer.py │ │ └── auditor.py │ ├── evaluation/ │ │ ├── fidelity.py │ │ ├── validity.py │ │ ├── privacy.py │ │ ├── fairness.py │ │ ├── utility.py │ │ └── cost.py │ ├── storage/ │ └── cli/ ├── experiments/ │ ├── baselines/ │ ├── ablations/ │ └── final/ ├── tests/ └── docs/